## Bug Reports
ID | Issue Title | UserRole | Description | Page/Screen | Steps to Reproduce | Expected Result | Actual Result | Severity | Screenshot Link | Status | Reported On | fixed On | By
ui001 | Admin sidebar collapse button not working |  | After logging in as Admin, the sidebar remains expanded and the collapse/expand toggle button does not respond, while all other sidebar navigation buttons work normally. | Admin Dashboard → Sidebar |  | Clicking the collapse icon should minimize/close the sidebar smoothly. | Collapse button does nothing; the sidebar remains stuck in expanded state. | Medium |  | Fixed |  |  | vvb
ui002 | go to dashboard button issue |  | after login, in the home page of the organiser, go to dashboard button is not navigating to the dashboard. | homepage(every role) |  | go to dashboard | page not found | High | https://drive.google.com/file/d/1mfrYFxj8t6d7_-jTVezyh44nBMT8nY1S/view?usp=drive_link | Fixed |  |  | vvb
ui003 | login button on the register college card |  | after login, there should not be a button to login. | homepage -> bottom most card |  | no login button | there is login button | Low | https://drive.google.com/file/d/1ulxOgLzKTVvbZAafNg-Ko1AigDOFmEEf/view?usp=drive_link | Fixed |  |  | vvb
ui004 | search icon on the search events search bar |  | the icon and the text are overlapping | eventspage |  |  |  | Low | https://drive.google.com/file/d/1IqwlPEwACj9i08BIGMcJ9UjIz-mOnAuS/view?usp=drive_link | Fixed |  |  | vvb
ui005 | show password icon issue (signup) |  | the show password icon is not showing up when clicked on the passoword tab. | sign up page | fill out all credentials, fill passwords, go again to the password tab. |  |  | Medium | https://drive.google.com/file/d/17CD3ys1D0-nI3OJ20JVMjSb5S12eN1NJ/view?usp=drive_link | Fixed |  |  | vvb
ui006 | preference settings not getting saved |  | in every user role, the settings are not getting saved. | settings page |  | saved settings | no response | High |  | Closed |  |  | vvb
ui007 | search bar is not working in all the tabs of the navbar |  | when searched for something and clicked on enter we are getting a 404 error. | navbar (all the tabs) |  | getting the cards of the searched item | 404 | High |  | Fixed |  |  | vvb
ui008 | theme is not changing | [6 empty] | Medium |  | Fixed |  |  | vvb
ui009 | No username in the settings (all roles) |  | At the time of registration, we are entering the user name too. but it not saved in the settings. (saved correctly in the database) | settings->general |  | username displayed as entered at the registration step. | nothing displayed | Medium |  | Closed |  |  | vvb
ui010 | organiser sidebar collapse button not working |  | in the organiser role, the sidebar is stays open up on clicking the dashboard and the admin panel and the collapse button is not working | user dashboard, user admin panel | click on the settings/inbox and then click on the dashboard or the admin panel icons. | the sidebar stays closed till manually opened by the user | the sidebar expanding and the collapse button not working | High | https://drive.google.com/file/d/1agH1w9VxR1xrfxRhgrsm9PgxASwc-op5/view?usp=drive_link | Fixed |  |  | vvb
ui011 | create team and create event buttons not working (organiser) | All | in the dashboard of the organsier, the create team and the create event buttons are not working. | dashboard (organiser) |  | opening the create modal | no response | Medium |  | Fixed |  |  | vvb
ui012 | search bar not present in the sponsor section |  | when opened the site , and clicked on the "sponsor" in the headbar ; doest not show search bar there unlike in events | HomePage before logging in |  |  |  | Low |  | Fixed
ui013 | Email Id not saved | Sponsor | when saving as a draft email the sender has to re-enter recipient's email. | Inbox(sponsor) |  |  |  | Low | https://drive.google.com/file/d/1JBMy68Ou8f8rnNdmWxfDxFpQxA3uylbb/view?usp=drive_link | In Progress
ui014 | Send button still grey | Sponsor | Upon entering the email of recepient , the send button doent not turn on untill enter is pressed; user may be anware of this fact | Inbox(sponsor) |  |  |  | High | https://drive.google.com/file/d/1yNupX1yyKAEeXKpSN9coZMFWoxpKfcI8/view?usp=drive_link | Fixed
ui015 | not able to send mail | Sponsor | not able to send mail currently in the inbox | Inbox(sponsor) |  |  |  | Critical |  | Fixed
ui016 | "add" button not functional yet | Sponsor | "add" button in the sponsor admin panel for uploading the image as well as video is not functional | Admin Panel(sponsor) |  |  |  | High
ui017 | cropping of poster | Sponsor | after publishing the ad in admin panel of sponsor the image is cropped ; ponsors might not be aware of this | Admin Panel(sponsor)(Published) |  |  |  | Low | https://drive.google.com/file/d/1JkrWpcxv3vzt9Zk9e9548qzbtBmJbpSo/view?usp=drive_link
ui018 | No preview of image in drafts | Sponsor | Image preview is visible oly when clicked the ad on draft and not in the overall screen | Admin Panel(sponsor)(Drafts) |  |  |  |  | https://drive.google.com/file/d/1CS8p7CJsmUh-xj6gtIGUAUSkreLf9q9A/view?usp=drive_link
ui019 | "interests" Section in sponsor | Sponsor | the sponsor profile doesnt necessarily require "interests" field as it was designed for organizers and students | Profile(sponsor)
ui020 | drafted ad shows up | all | the ads that were in draft shows up in the common "sponsors" page though after clicking on it says "ad not available" | Sponsors listing page |  |  |  |  | https://drive.google.com/file/d/1u0KvtHbGp_8p_x1hjWmZJNU2l2DnRPKT/view?usp=drive_link
ui021 | The back button is not functional | all | The back button is not functional in the page which it takes to after clicking on " learn more" below the ad | Sponsors listing page |  |  |  |  | https://drive.google.com/file/d/1mijR097kQPzN9y0p-2dj_wIAq8HSirno/view?usp=drive_link
ui022 | The draft ad shows up | all | The draft ad shows up on clicking "viewads" option in sponsor listing page ; which should not since it is a draft | Sponsors listing page
ui023 | Color inconsistency in the login box | all | when selected from the saved mails in the browser, the color in the email box changes to white. | login page/signup page | while filling the email, select from the save mails | no colour change | colour change. | Low | https://drive.google.com/file/d/1JgxY2tU1LaOrWCywxcNChPB6MLh8dXCF/view?usp=drive_link | Fixed
ui024 | The mail details are out of bounds | admin |  | inbox |  |  |  | High | https://drive.google.com/file/d/12aGuKHxor-KQyGjzWwSnZ7hjERyRUbHR/view?usp=drive_link | Fixed
ui025 | settings page not worjking | [8 empty] | Fixed
ui026 | save changes button not at the ergonomic position.
ui027 | all events button is required. |  |  | events details page |  |  |  | Medium |  | Fixed
ui028 | events details page dark theme integration is not done. | [6 empty] | Low |  | Fixed
ui029 | college registration link checking
ui030 | student sign up page doesnt notify what went wrong | student | when we enter details and click on sign up if any detail like email password is wrong it does not register you instead it should show like password should contain one captial or email is wrong etc. | student sign up | add a notification notifying the next step to the user | email not valid/ password must follow the format etc | nothing show up leaving the user confused | Medium |  | Fixed |  |  | ts
ui031 | The map is not working | all | when clicked on the map option in the event details page the page is not loading ->going blank | eventdetails page ->map |  |  |  | Critical
ui031 | Forgot Password not working | all | when clicked on forgot password and clicked on get OTP; server error showed up | sponsor sign up |  |  |  | Critical | https://drive.google.com/file/d/1JDkGLz9hDySqsTPxpJXvfLRcsMcuAXEh/view?usp=drive_link
ui032 | no dashboard button to easily navigate | all | always if a person wants to go to the dashboard, chose profile from icon and then go to the dashboard. |  |  |  |  | High |  | Fixed
ui033 | The Date of event is messed up | Organizer | while creating the event,on clicking the date it shows up a messed up calender | Admin Panel Organizer |  |  |  |  | https://drive.google.com/file/d/1KHbRw1t28kzvO4rwECZk5WtamjygM1_V/view?usp=drive_link
ui034 | Save changes button not functional | Organizer | while editing a draft event after making changes and clicking on "save changes" does not work. | Admin Panel Organizer |  | Edited portion updated | Shows old details | High
ui035 | Buttons for map anottations not working | Organizer | after creation of draft event, map option is chosen which opns into a worlwide map;though buttons for "set a location", "save", "delete" not working | Admin Panel Organizer |  | map annotted | no anottation seen | High | https://drive.google.com/file/d/1q0UW81S3VfZsZZcfw9HoCASAraxT5aeI/view?usp=drive_link
ui036 | Deleted team shows | Organizer | while creating event and selecting the team for event , a previously deleted team (codecrafters) shows up in drop down | Admin Panel Organizer |  | Only non deleted team to show | Deleted teams in drop down | Medium | https://drive.google.com/file/d/1sl4sZtC1gZ6HsS0FQka0pMAToYzhslUg/view?usp=drive_link
ui037 | Shows an event is live even though date is in future | Organizer | The event which has start date as 1st dec 2025,is showing live today is 29 th nov | Admin Panel Organizer | in the organizer dashboard in Events menu and live submenu | should not show live yet | Shows live | High | https://drive.google.com/file/d/1lWcwXWPymnM5s0f2b3WvxNi7LgosAaW9/view?usp=drive_link
ui038 | otp already sent scenario | all | there is no placeholder to fill the otp once a user gets out of the flow |  |  |  |  | Medium |  | Fixed
ui039 | show password icon issue (forgot password) | all | there is no option to show/hide password |  |  |  |  | Medium |  | Fixed
ui040 | UI problem in event decsp | Organizer | the description is shown in one line only not in paragraph form | Organizer Admin Panel->events menu->published submenu |  |  |  | High |  | Fixed
ui041 | "view report" not working | Organizer | View report button not functional in the completed events in admin panel of organizer |  |  | should show report | button not working
ui042 | "edit configuration" button not working | Oragnizer | edit configuration button in admin panel->registration menu->event card->view | Admin Panel Organizer
ui043 | registration for the event not working | student
ui044 | Notif bell does not show new mails | organizer | a team invite was sent by org1 to org2 and so on but in org 2 profile the bell icon didnot show a superscript as 1 | Home page ->bell icon |  | should show 1 | is not showing 1 | Medium
ui45 | the uploaded poster not showing up | organiser |  |  |  | should show 1 | not showing | Medium
ui46 | same event name cant be uploaded | organiser | same event name shouldnt be shown avaiable but its showing available |  |  | should not show | is showing avaialble | Medium
ui47 | past dates must show error | organiser | added the past date but not showing any error |  |  | should show error | not showing error | Low

## Test Cases
Test Case ID | Test Scenario | Page/Screen | Pre-Conditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments | Resolved | Done By
TC_LOGIN_01 | User sign up | Login Page | user does not exist. |  |  | creat admin user with a key | created admin user | Pass | key/code not yet created | N/A | Bvv
tc_login_02 | user sign up | login page | user does not exist. | fill out two differnt passwords |  | dialog box saying the password does not match | no dialog box, no error message | Fail |  | Yes | bvv
tc_login_03 | student sign up | login page | user does not exist. |  |  | create student user | created student user | Pass |  | N/A | bvv
tc_login_04 | sponsor sign up | login page | user does not exist. |  |  | create sponsor | created sponsor | Pass |  | N/A | bvv
tc_login_05 | sign up | login page | user does not exist. | fill out invalid passowrord |  | dialog box saying the password does not meet conditions | no dialog box, no error message | Fail |  | Yes
email sending is working for the sponsors